## Slide 1
Modernizing Meridian's Inventory Dashboard
Capabilities Presentation | RFP MC-2026-0417
Prepared for Meridian Components, Inc. • April 27, 2026

## Slide 2
ACT 1 — UNDERSTANDING
What we heard from Meridian
• Operations runs the business through this dashboard — every day, three warehouses
• Reports module has known defects the previous vendor never closed out
• Restocking workflow VP Operations has been asking for doesn't exist yet
• No automated tests — IT has frozen further change until that's resolved
• The system works, but it can't safely evolve. That's the gap we close.

## Slide 3
SCOPE
Required deliverables
• R1 Reports module remediation — audit + fix the 8+ logged defects
• R2 Restocking recommendations — budget-aware PO engine, operator-in-control
• R3 Automated browser tests — coverage on the flows that matter
• R4 Architecture documentation — IT-ready handoff, week one

## Slide 4
SCOPE
Desired — where they fit naturally
• D1 UI refresh — modernize layer above your existing slate/gray tokens
• D2 Internationalization — Japanese for Tokyo, scaffold for future locales
• D3 Dark mode — operator-selectable, useful on warehouse floor stations
• We bring these in during Phase 3 only if Phase 1–2 land clean.

## Slide 5
HOW WE WORK
Our approach
• Tests aren't a deliverable at the end — they're how we work each week
• Architecture review week one, before we touch a line of code
• Restocking is designed around the operator, algorithm proposes, human decides
• Weekly demos with R. Tanaka. Defect log shared from day one.
• Predictable cadence. No surprises in week eight.

## Slide 6
TIMELINE
10 weeks, three phases
Phase 1 — Foundation (wks 1–3)
• Architecture review (R4)
• Reports audit & remediation (R1)
• First E2E test suite (R3)
• Milestone: green build, IT sign-off
Phase 2 — Build (wks 4–7)
• Restocking recommendation engine (R2)
• Budget ceiling + demand forecast
• Operator override workflow
• Milestone: Tanaka demo & UAT

## Slide 7
TIMELINE
Phase 3 — Polish & handoff (wks 8–10)
• Hardening, performance pass, accessibility check
• Desired items where they fit (D1 / D2 / D3)
• CI integration with Meridian IT
• Final architecture handoff document
• Milestone: production cutover, warranty period begins

## Slide 8
INVESTMENT
Pricing
• Fixed-fee: $148,000
• Billed against four phase milestones, not hours
• Includes all required items (R1–R4) and Phase 3 desired items where they fit
• 30-day warranty period post-cutover included
• Out of scope: net-new modules beyond Restocking, ERP integration, data migration

## Slide 9
WHY US
What you get with this team
• We leave codebases better-documented than we found them
• Tests-as-we-go, not tests-at-the-end
• Operator-centric design — your team stays in control
• Predictable weekly cadence, no week-eight surprises
• Direct line to senior engineers — no handoff to junior staff post-sale

## Slide 10
Let's make the next change a green build.
Questions, clarifications, next steps — we're ready when you are.
RFP MC-2026-0417 • Response due May 8, 2026